## Active Projects
| Date Requested | Primary Requestor/Client | Project Name | Funding Source | Status | Approvals needed to proceed | Design Progress | Const'n Progress | Due Date | Description | Project Budget | Budget Change | New Budget | Start Date | Est. Compl. Date | PM/Contact | Designer of Record | Contractor | Comments
1 | 2022-07-18 | Athletics | Baseball Centerfield Wall | TBD | 0 Requesting | OSA | 10 | 10 | NA | Installation of a 30' x 70' centerfield wall. | 200000 | 0 | 0 | TBD | TBD | NA | RBA | TBD | Submitted to THEC for Oct. 1 meeting.
2 | 2022-07-18 | Athletics | Scope & Estimating Hand Baseball Artificial Turf Installation | TBD | 0 Requesting | Board/THEC/SBC | 10 | 10 | 2022-10-21 | Installation of new artificial outfield turf | 2000000 | 0 | 0 | TBD | TBD | NA | TBD | TBD | May be incorporated into Baseball Outfield Drainage. This project should be coupled with the outfield drainage project, currently in feasibility. Project budget was provided by Athletics at $1.5m, but needs to be verified. Similar scope cost TTU $2.26m.
3 | 2022-09-09 | Athletics | Video Board Installation | TBD | 0 Requesting | THEC/OSA | 10 | 10 | 2022-11-14 | Replacing the scoreboard in Fortera with a video board | 750000 | 0 | 0 | TBD | TBD | TBD | TBD | TBD | Will be submitted to THEC in November
4 | NA | Student Affairs | C. E. Harvill Food Venue | Gift-in-Place | 0 Requesting | OSA | 33 | 10 | 2022-11-09 | Build-out of interior for new food venue | 3800000 | 0 | 0 | 2022-11-22 | 2023-08-23 | NA | Sodexo | Sodexo | Project is designed & delivered by Sodexo, food service provider. Roof will be replaced after penetrations are made. The 11/9/22 date is the latest the project can be submitted, approved by CPDC, OSA and still start construction in January. A later start may impact the August opening date.
5 | 2019-10-30 | Student Affairs | Pan Hellenic Plaza | Gift | 0 Requesting | OSA | 10 | 10 | NA | Construction of Greek monuments between Marks & Blount. | 300000 | 0 | 0 | TBD | TBD | TBD | TBD | TBD | Submitted to THEC for Oct. 1 meeting. Greek Affairs is beginning fund raising. Conceptual design and estimate is complete.
6 | 2020-10-19 | Athletics | Athletics Student Success | TBD | 0 Requesting | THEC/OSA | 10 | 10 | 2022-11-14 | Interior renovation of Downey shell space for student success | 900000 | 0 | 0 | TBD | TBD | TBD | TBD | TBD | Will be submitted to THEC in November
7 | NA | Capital Maint. Request | Sundquist Roof | State | 0 Requesting | THEC/SBC | 95 | 10 | NA | New standing seam roof | 3285000 | 2128000 | 5413000 | 2023-07-01 | TBD | PZ | LCM | TBD | Deferred pending additional funds
8 | 2022-08-12 | Academic Affairs | Scope & Estimate Grasslands Institute Renovations | TBD | 2 Planning | NA | 10 | 10 | NA | Scope & estimate to make improvements to the lower level of the Welcome Center | TBD | 0 | 0 | TBD | TBD | PZ | TBD | TBD
9 | 2022-07-02 | Academic Affairs | Scope & Estimate-Farm Trough Additions | TBD | 2 Planning | NA | 10 | 10 | NA | Scope & estimate to add 3 troughs and water supply at farm | TBD |  |  | TBD | TBD | YW | Genesis | TBD | Project will have a second phase to add three watering troughs.
10 | 2022-03-21 | F&A | Scope & Estimate College & Fourth 2nd Floor Renovation | Plant Funds | 2 Planning | SBC | 10 | 10 | NA | Renovation of second floor and portion of first floor | 1750000 | 0 | 0 | TBD | TBD | TBD | TBD | TBD | Board approved on June 10, 2022. Awaiting funding. Will free-up space on 1st floor of east side of Browning and Procurement
11 | NA | Other | Hayes House Property Disposal | NA | 2 Planning | ESC | 10 | 10 | TBD | Sell property | NA | NA | NA | NA | NA | NA | NA | NA | Procurement Services is contacting STREAM to start the process. Will eventually have to be approved by SBC. To date, capital investment has been $447,938.85. APSU purchased the property in 2017 for approx. $350,000, with a gift from the owner for approx. $300,000.
12 | 2022-07-18 | Athletics | Scope & Estimate Softball Batting Expansion | Gift | 2 Planning | NA | 10 | 10 | NA | Add 12' pitching lane expansion along east side. | TBD | 0 | 0 | TBD | TBD | TBD | TBD | TBD | Project may also include lighting, electrical, and heating.
13 | 2022-07-18 | Athletics | Scope & Estimate Softball Dugouts | TBD | 2 Planning | NA | 10 | 10 | NA | Replace dugouts with recessed ones with restrooms. | TBD | 0 | 0 | TBD | TBD | TBD | LCM | TBD | Considered a new structure. Awaiting funding
14 | 2022-04-21 | Athletics | Scope & Estimate-Baseball Outfield Drainage | TBD | 2 Planning | NA | 10 | 10 | NA | Scope & estimate to mitigate outfield drainage issues | 1000000 | 0 | 0 | TBD | TBD | NA | TBD | TBD | Will be incorporated into Baseball Artificial Turf
15 | 2022-03-10 | Athletics | Scope & Estimate-East Side Stadium HVAC | TBD | 2 Planning | NA | 10 | 10 | NA | HVAC study | TBD | 0 | 0 | TBD | TBD | NA | Genesis | TBD
16 | NA | Capital Outlay Request | Scope & Estimate Student Success | State/APSU Match | 2 Planning | NA | 10 | 10 | NA | Conversion of Memorial Health to Student Success | TBD | 0 | 0 | TBD | TBD | MB | TBD | TBD | Relocate all of Student Success, Honors, PELP, SRC in Memorial Health, and demolish Marks. This will be a capital outlay request.
17 | 2022-09-22 | F&A | Campus HVAC Study | TBD | 2 Planning | NA | 10 | 10 | NA | Campus-wide study of HVAC needs | TBD | 0 | 0 | TBD | TBD | TBD | TBD | TBD
18 | 2022-09-02 | Physical Plant | Scope & Estimate Campus Site Lighting | TBD | 2 Planning | NA | 10 | 10 | NA | Site lighting Improvement at various locations | TBD | 0 | 0 | TBD | TBD | TBD | Genesis | TBD
19 | 2022-08-11 | Physical Plant | Scope & Estimate MMC North and East entrance repairs | TBD | 2 Planning | NA | 10 | 10 | NA | Replacing stairs, and repairing masonry at adjacent wall | TBD | 0 | 0 | TBD | TBD | TBD | TBD | TBD
20 | 2022-09-07 | Physical Plant | Scope & Estimate MMC Stage Doors | TBD | 2 Planning | NA | 10 | 10 | NA | Modify 52' tall stage doors. | TBD |  |  |  |  | MB | TBD | TBD | Doors are too narrow at the top so the rigging cabling can't fit, the the rigging is too low. Doors will be modified to accommodate rigging cabling.
21 | 2022-09-29 | Physical Plant | Scope & Estimate Sentinel Plaza Improvements | Plant Funds | 2 Planning | NA | 10 | 10 | TBD | New and replaced hardscaping & flatwork | TBD
22 | 2022-06-16 | Residence Life | Scope & Estimate-Meacham Drainage | TBD | 2 Planning | NA | 10 | 10 | NA | Scope & estimate to divert water to retention pond | TBD | 0 | 0 | TBD | TBD | NA | TTL | TBD
23 | NA | NA | Campus Master Plan | Plant Funds | 3 RFQ/Contracting | All approvals rec'd | 10 | 10 | NA | Prioritizing capital projects, teaching space, office & remote work space study, facilities condition report, maintenance schedules, general campus planning, incorporation of other studies | 500000 | 0 | 0 | 2023-03-01 | 2024-08-01 | MB | TBD | NA | Designer solicitation begins in November
24 | NA | Capital Maint. Request | Dunn HVAC | State | 4 Design | All approvals rec'd | 50 | 10 | NA | Replace HVAC, electrical feeds, & fire alarms | 5295000 | 4000000 | 9295000 | 2022-07-01 | 2025-08-01 | PZ | SSR | Barton Mallow | Will be completed in two phases, with construction beginning spring 2023. Completion dependent upon state funding.
25 | NA | Capital Maint. Request | Elevator Upgrades | State | 4 Design | All approvals rec'd | 10 | 10 | NA | Update elevators in Claxton, Trahern, Dunn, UC | 1000000 | 0 | 0 | 2022-08-01 | TBD | YW | KMBG | TBD | Updated elevators for
26 | NA | Academic Affairs | University Welcome Center | Plant Funds | 4 Design | All approvals rec'd | 33 | 10 | NA | Renovation & exterior upgrades in old Honda dealership | 2500000 | 0 | 0 | 2022-07-01 | 2024-02-01 | PZ | WBA | TBD
27 | NA | Capital Outlay Request | Health Professions Building | State/APSU Match | 4 Design | All approvals rec'd | 33 | 10 | NA | Construction of 114,600 SF bldg to house Nursing, Health & Human Performance, Social Work, Med Lab Science, & Psy. Counseling | 71887500 | 32000000 | 103887500 | 2022-07-01 | 2025-03-01 | PZ | Hastings | Messer | Project design will restart Aug. 2022 with construction starting July 2023 assuming full funding.
28 | NA | Capital Outlay Request | Kimbrough Classroom Renovations | State/APSU Match | 4 Design | All approvals rec'd | 33 | 10 | NA | Interior renovation & ADA addition | 9200000 | 0 | 0 | 2022-07-01 | TBD | PZ | RJA | TBD
29 | 2021-03-24 | Academic Affairs | Farm Water Pressure | Plant Funds | 5 Bidding/Contracting | All approvals rec'd | 95 | 10 | NA | Increasing water pressure on farm | 70000 | 0 | 0 | 2022-08-01 | 2022-12-01 | YW | Genesis | TBD | Project will have a second phase to add three watering troughs.
30 | 2022-04-05 | F&A | 415-417 N. 2nd St. Demolition | Plant Funds | 5 Bidding/Contracting | All approvals rec'd | NA | 10 | NA | Demolition of building in preparation to create parking lot. | 65000 | 0 | 0 | 2022-10-23 | 2022-11-24 | WP/PP | NA | TBD | Demo can begin 10/24/22
31 | NA | Capital Maint. Request | Music Mass Comm HVAC | State | 6 Construction | All approvals rec'd | 95 | 75 | NA | Replace HVAC system | 2730000 | 0 | 0 | 2015-06-02 | 2023-03-30 | PZ | ICT | SM Lawrence | TBR Managed
33 | NA | Capital Maint. Request | Sundquist Exhaust Controls | State | 6 Construction | All approvals rec'd | 50 | 75 | NA | Replace ventilation controls making fume hoods work with building HVAC | 1500000 | 0 | 0 | 2021-07-21 | 2023-01-01 | PZ | HNA | Xenergy | Only 1/3 of the project will be done due to budget. Additional funds will be requested from the state in the future.
35 | 2021-05-17 | Athletics | Baseball Practice Facility | TBD | 8 On hold | Board/THEC/SBC | 10 | 10 | NA | Replacement of baseball batting facility | 2725634 | 0 | 0 | TBD | TBD | TBD | TBD | TBD | Awaiting on funding source.
36 | 2022-07-18 | Athletics | Scope & Estimating Cathi Maynard Softball Artificial Turf Installation | TBD | 8 On hold | NA | 10 | 10 | NA | Installation of new artificial outfield turf | TBD | 0 | 0 | TBD | TBD | NA | TBD | TBD | Project budget was provided by Athletics at $1.5m, but needs to be verified. Similar scope cost TTU $2.26m.
37 | 2022-02-25 | Athletics | Softball Outfield Stands | TBD | 8 On hold | THEC/OSA | 10 | 10 | NA | Construction of new outfield seating for softball | 705000 | 0 | 0 | TBD | TBD | NA | RJA | TBD | Considered a new structure. Awaiting funding
38 | 2021-04-19 | Parking Services | Lot 7 | Aux. | 8 On hold | All approvals rec'd | 95 | 10 | NA | Reorient, resurface, landscape, new lighting, walks | 750000 | 480000 | 1230000 | 2023-05-01 | 2023-08-01 | NA | Hurst Rosche | TBD | Submitted to SBC for October meeting to increase funding