## 00 63 57 CHANGE ORDER REQUEST
Date: |  | 2012-12-12
Project No.: |  | XXX/XXXXX-XXXX |  |  |  |  | Change Request No.: |  |  | 4
Project Title: |  | PROJECT NAME |  |  |  |  | Construction Completion % |  |  | 78%
Facility Name: |  | BLDG |  |  |  |  | Target Substantial Completion |  |  | 2017-01-12
Designer |  | DESIGN FIRM
Contractor |  | GC
This Change Order Request (Proposal) contains an itemized quotation for changes in the Contract Sum and/or Time in response to proposed modifications to the Contract Documents based on Proposal Request No. or other conditions which require this Proposal.
Description of Proposed Change:
This Change order will modify the Contract time and/or Contract sum due to the following <<RFP's, Designer Recommendation>>. EXAMPLE
Reason for Change:
RFP # | JUSTIFICATION
12 | RFP modifies the Contract time and/or Contract sum for the Labor and Materials neccesary to <<>>
BASE CONTRACT AMOUNT (BCA) |  | 18000000 | THIS CHANGE ORDER |  |  | ALL PRIOR CHANGE ORDERS |  |  | CHANGE ORDER TOTALS
RFP # | Initiating Entity | Cause | Time/Days | Cost | % BCA | Time/Days | Cost | % BCA | Total Time/Days | Total Cost | % BCA | Select | Select
24 | External Factors | Unavoidable Delays | 22 | 3000000 | 16.67% | 12 | 12222 | 0.0679% | 34 | 3012222 | 16.73% | Hidden Conditions | External Factors
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Codes (provide code regulation) | Designer
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Unavoidable Delays | Owner
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Designer
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Error
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Omission
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Schedule Modifications
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Added Scope
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Cost Efficiencies
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0% | Value Added
| Select | Select |  |  | 0% |  |  | 0% | 0 | 0 | 0%
Total Modifications |  |  | 22 | 3000000 | 16.67% | 12 | 12222 | 0.0679% | 34 | 3012222 | 16.73%
| The new Contract sum, including this modification |  |  |  |  | 21012222
| The new Contract Time, including this modification | [5 empty] | 2017-02-15
Submitted By:
Email:
Phone:

## 00 63 63 FORM FOR CO OR CD
|  | Amendment |  |  |  | This Change initiated: |  |  | 2017-06-02
| X | Change Order |  |  |  | Modification Number: |  |  | 4
|  | Construction Change Directive |  |  | Project: |  | PROJECT NAME
| Original Contract Date: |  |  | 2017-01-12
| Original Contract Sum: |  |  | 18000000 |  | Project Number: |  | XXX/XXXXX-XXXX
The following changes in the Contract are hereby directed:
RFP # |  | SUMMARY |  |  |  | Cost |  | Time/Days | %
24 |  | RFP modifies the Contract time and/or Contract sum for the Labor and Materials neccesary to <<>> |  |  |  | 3000000 |  | 22 | 16.67%
0%
0%
0%
0%
0%
0%
0%
0%
[9 empty] | 0% | increases
[9 empty] | 0% | does not change
[6 empty] | Cost |  | Time/Days | %
| This modification |  | increases | the Contract Sum |  | 3000000 |  |  |  | decreases
| This modification |  | increases | the Contract Time |  |  |  | 22
| This modification |  | increases | the Change Order Percentage |  |  |  |  | 16.67%
| Net Change previously authorized |  |  |  |  | 12222
| Percentage of Previous Change Orders | [7 empty] | 0.0679%
| The Contract Sum prior to this Modification |  |  |  |  | 18012222
Contingency Prior to this Modification
| The new Contract sum, including this modification |  |  |  |  | 21012222
The new Contingency Amount
| New Percentage of Change Orders including this Modification | [7 empty] | 16.73%
| The new Contract Time, including this modification | [6 empty] | 34
| The last day of the Contract Time, including this modification |  |  |  |  | 2017-02-15
| Contractor |  |  | Designer |  | Owner
signed |  |  |  | signed |  | signed
name |  |  |  | name |  | name
title |  |  |  | title |  | title
for |  |  |  | for |  | for
Additional Owner signatures (as required):
signed |  |  |  | signed |  | signed
name |  |  |  | name |  | name
title |  |  |  | title |  | title
for |  |  |  | for |  | for

## 00 63 63.1 CO SUMMARY
SPA |  |  |  |  | Owner/User Agency |  | Austin Peay State University
Project Title | PROJECT NAME |  |  |  | Location |  | BLDG
SBC No. | XXX/XXXXX-XXXX |  |  |  | Subprojects |  |  |  | Single |  | Multiple
| Bid Target | MACC |  |  | Contingency |  |  |  | % of Bid Target:
Master Project
Subproject #
Undedicated Funds |  | Provide a summary of sources of undedicated project funds:
Designer | DESIGN FIRM |  | Construction Completion % |  |  |  |  | 78%
Contractor | GC |  | Target Substantial Completion |  |  |  |  | 2017-01-12
Base Contract Amt | 18000000 |  | This Change Order # |  |  | 4 |  | Total Change Orders (including this one)
Initiating Entity | Cause |  | Time | Cost |  | % BCA |  | Time |  | Cost | % BCA
External Factors | Unavoidable Delays |  | 22 | 3000000 |  | 16.67% |  | 34 |  | 3012222 | 16.73%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
Select | Select |  | 0 | 0 |  | 0% |  | 0 |  | 0 | 0%
TOTAL |  |  | 22 | 3000000 |  | 16.67% |  | 34 |  | 3012222 | 16.73%
| Total Change Orders (including this one) |  |  | 3012222
| Revised Contract Amount |  |  | 21012222
Provide a summary justification for the current Change Order to be approved:
This Change order will modify the Contract time and/or Contract sum due to the following <<RFP's, Designer Recommendation>>. EXAMPLE
Submitted by:
Approved:
Approved:
Owner/User Agency: